## Overview
AI Digital Archive (IDP) — MVP Roadmap
Agile delivery plan • MoSCoW prioritization • 9-week timeline • 2-person team
Target timeline | 9 weeks
Team | 2 IT professionals (Dev A = SaaS/full-stack, Dev B = AI/IDP pipeline)
Methodology | Agile — short sprints (≈2 weeks) + MoSCoW feature prioritization
MVP thesis | Archive-first. Build the ~85% 'boring SaaS' (auth, tenancy, storage, search, retrieval) and prove it end-to-end BEFORE the AI layer. IDP ships as a thin slice.
Top constraint | Cost-efficiency for both storage and AI processing is the #1 priority.
Scope warning | 9 weeks for 2 people is aggressive. The Won't-Have list is what protects the timeline — treat it as binding, not aspirational.
How to read this workbook
MoSCoW Prioritization | What we build now vs. defer vs. explicitly skip.
Roadmap & Milestones | Sprint-by-sprint plan with one measurable deliverable per sprint.
Tech & Resources | The few tooling decisions that make or break a 2-person, 9-week build.
Success Metrics (KPIs) | How we'll know within ~4 weeks of launch whether the MVP works.

## MoSCoW Prioritization
ID | Priority | Feature | Description | Why it's here | Target release
M1 | Must | Authentication & login | Email/password login, password reset, sessions, basic roles (admin/user). | Entry gate to a multi-tenant system; security baseline. | MVP
M2 | Must | Multi-tenancy (Postgres RLS) | tenant_id on every row; row-level-security policies enforce isolation at the DB. | Core SaaS requirement — client data must never leak across tenants. | MVP
M3 | Must | File upload (PDF, scanned PDF, images) | Single + small batch upload of the stated formats to object storage. | The product's front door; must accept the real input types. | MVP
M4 | Must | Secure storage + metadata | Bytes in S3-compatible storage, encrypted at rest; metadata row in Postgres. | Cheap, durable storage; never store files in the DB. | MVP
M5 | Must | Async processing pipeline | Queue + worker. Upload returns instantly; processing runs in background. | Decouples slow IDP from fast archiving — key to cost and UX. | MVP
M6 | Must | Text extraction (text-layer + OCR) | PyMuPDF for digital PDFs; PaddleOCR fallback for scans/images. | Produces the searchable text — the foundation of retrieval. | MVP
M7 | Must | Structured extraction — thin slice | VLM-to-JSON for 1–2 document types (e.g. invoice, PO) against a fixed schema. | Demonstrates the IDP value at minimal scope and cost. | MVP
M8 | Must | Search & retrieval | Filename (fuzzy), full-text content, and metadata filtering via Postgres. | The core archive value: users must find files fast and accurately. | MVP
M9 | Must | Document viewer + download | View original file and its extracted JSON; download the original. | Closes the loop: store → find → retrieve. | MVP
M10 | Must | Basic web UI | Upload, list, search, view screens. Minimal, clean styling. | A usable interface for the pilot client. | MVP
S1 | Should | Classification + layout fingerprint | Detect document type and 'have we seen this layout?' before extraction. | Unlocks the cheap deterministic path; cuts GPU cost. | V1.1
S2 | Should | Deterministic extraction path | Anchored-field / template extraction for known layouts (no GPU). | The main unit-cost saver once volume grows. | V1.1
S3 | Should | Confidence scoring + exception queue | Flag low-confidence docs (~2–5%) for light human review. | De-risks silent extraction errors at tiny cost. | V1.1
S4 | Should | Manual correction UI | Let users edit extracted fields and re-save. | Improves trust and the quality of stored data. | V1.1
S5 | Should | Audit log & activity history | Record who uploaded / viewed / downloaded what, and when. | Expected by auditor and legal clients (PDPA posture). | V1.1
S6 | Should | Bulk / folder ingestion | Drag many files or a zip; queue them all. | Throughput needed for real client onboarding. | V1.1
C1 | Could | Promotion of novel types | After N clean examples, auto-derive a cheap extractor for a new type. | The compounding cost flywheel (GPU → CPU over time). | V2
C2 | Could | Client template/schema manager | Clients self-define their own document types and fields. | Self-service scaling beyond a fixed schema set. | V2
C3 | Could | Storage cold-tiering | Move rarely-read files to an archive storage tier automatically. | Storage cost optimization once read patterns are known. | V2
C4 | Could | Analytics dashboard | Volumes, accuracy, and cost-per-doc views. | Operational visibility for the team and clients. | V2
C5 | Could | Public API / webhooks | Programmatic ingest and retrieval; event callbacks. | Integration with client systems. | V2
C6 | Could | Notifications | Email / in-app 'your document is processed'. | UX polish; not core to validation. | V2
W1 | Won't | Dedicated-instance tenant isolation | Pooled RLS is sufficient for MVP; revisit for regulated clients. | Avoids per-tenant infra cost and ops in MVP. | Out of scope
W2 | Won't | Elasticsearch / OpenSearch cluster | Postgres full-text search is enough at this volume. | Removes a heavy standing service and its cost. | Out of scope
W3 | Won't | Microservices architecture | Ship a modular monolith + one worker. | Microservices multiply infra and debugging for no MVP benefit. | Out of scope
W4 | Won't | Multi-region / DR failover | Single region for MVP. | Cost and complexity not justified pre-product-market-fit. | Out of scope
W5 | Won't | Custom model fine-tuning | Use off-the-shelf open-weight models. | Fine-tuning burns time/budget before it's warranted. | Out of scope
W6 | Won't | SSO / SAML / advanced RBAC | Basic roles only. | Enterprise auth is a later, sales-driven need. | Out of scope
W7 | Won't | Mobile app | Web only. | Focus the tiny team on one surface. | Out of scope
W8 | Won't | Fully autonomous zero-review extraction | Keep a human-review option available; don't remove the safety net. | Silent wrong values on invoices/contracts are the worst failure. | Out of scope

## Roadmap & Milestones
9-week plan • ~2-week sprints • two parallel tracks (SaaS core + IDP) that converge in Sprint 3
Sprint | Weeks | Theme | Key tasks | Milestone deliverable (measurable) | Primary owner
Sprint 0 | Week 1 | Foundations & architecture | Provision cloud + Supabase + object storage + repo & CI. Finalize Postgres schema with tenant_id and RLS policies. Auth scaffold. Spike OCR (PaddleOCR) and the VLM on real sample docs. Lock the 3 critical decisions. | 'Walking skeleton' deployed: a user can sign up / log in; empty schema with RLS live; OCR + VLM spike runs on 1 sample document. | Both (A: infra, B: AI spike)
Sprint 1 | Weeks 2–3 | Core SaaS & ingestion | Enforce RLS multi-tenancy. User management. File upload (PDF / scanned PDF / image) to object storage. Metadata records. File list / view / download UI. | A tenant user can upload a file, see it listed, and download it. Cross-tenant access is blocked and proven by an automated isolation test. | Dev A (backend + UI)
Sprint 2 | Weeks 4–5 | Extraction pipeline | Queue + worker. Text-layer extraction (PyMuPDF). OCR fallback (PaddleOCR) for scans/images. Store extracted text. Push text into the search index. | Every uploaded file is processed asynchronously; its text is extracted and stored; processing status is visible in the UI. | Dev B (AI / pipeline)
Sprint 3 | Weeks 6–7 | Search + structured IDP | Postgres full-text (tsvector) + fuzzy filename (pg_trgm) + JSONB metadata filters + search UI. VLM-to-JSON for 1–2 document types against a fixed schema; show JSON in the viewer. | User finds files by name / content word / metadata in under ~2s; the supported document types return correct structured JSON. | Both (A: search/UI, B: extraction)
Sprint 4 | Week 8 | Hardening & security | End-to-end testing of all journeys. RLS isolation test suite. Error handling and retries in the pipeline. Basic logging + Sentry. Encryption-at-rest check. Bug fixing. | All MVP user journeys pass; tenant-isolation tests green; no open critical/high bugs. | Both
Sprint 5 | Week 9 | Pilot & launch | Deploy to production. Onboard 1 friendly pilot client. Load their real documents. Instrument the KPIs. Collect feedback. Buffer for slippage. | Pilot client is live and processing real documents; KPI instrumentation is collecting data from day one. | Both

## Tech & Resources
Area | Recommended choice for MVP | Rationale | Risk / note
Team structure | Dev A = full-stack / SaaS core; Dev B = AI / pipeline; share the frontend. | Two parallel tracks that converge at search + structured IDP. | 9 weeks for 2 is tight — protect scope; the Won't-Have list is the schedule's safety valve.
Backend framework | FastAPI (Python). | One language across SaaS and AI; fast to build and hire for. | —
SaaS backbone | Supabase (managed Postgres + Auth + RLS + Storage). | Collapses four services into one — the single biggest time-saver for a small team. | Some lock-in, but it's standard Postgres underneath, so exit is feasible.
Object storage | Supabase Storage or Cloudflare R2. | Zero / low egress, cheap, S3-compatible — fits unpredictable read patterns. | Defer cold-tiering to V2; don't pre-optimize storage now.
Database / search | Postgres: tsvector (full-text), pg_trgm (fuzzy filename), JSONB + GIN (metadata). | Meets all three search needs with zero extra infrastructure. | Only consider Meilisearch/Typesense if a corpus outgrows Postgres.
Job queue | Redis + RQ (or Celery). | Simple, proven async processing with minimal ops. | Keep worker concurrency modest at MVP volume (~1,000 docs/day).
Text extraction / OCR | PyMuPDF (text layer) + PaddleOCR / PP-Structure (scans, tables, multilingual). | Skipping OCR when a text layer exists is the biggest single cost saver; PaddleOCR covers Malay + English + CJK and tables. | Validate accuracy on real scanned Malay documents early in Sprint 0–2.
VLM (structured extraction) | Open-weight document VLM (Qwen2.5-VL class) via on-demand / serverless GPU. | Avoids paying for an always-on GPU during MVP; pay per use; model outputs JSON directly (no regex). | CRITICAL DECISION: move to self-hosted GPU later for cost/control. Benchmark 2–3 models on YOUR real docs before locking in.
Frontend | React / Next.js + a component kit (e.g. shadcn/ui). | Minimal, fast, presentable for a pilot. | Keep the UI spartan — it is not where MVP value lives.
Hosting / region | Single region — Malaysia or Singapore. | Data-residency posture for PDPA; low latency for local users. | Confirm PDPA cross-border rules with a Malaysian legal advisor before the first regulated client.
Error tracking | Sentry (free tier). | Catch pipeline failures fast with a 2-person team. | Optional but strongly recommended.
Three decisions to lock in Sprint 0 | (1) Supabase vs self-host; (2) serverless vs self-host GPU; (3) which 1–2 document types form the thin slice. | These three set the entire scope, cost, and risk profile of the MVP. | Decide before any feature code is written — changing them mid-build is the top schedule risk.

## Success Metrics (KPIs)
Track K1–K3 as the 2–3 core validation metrics; K4–K5 are supporting signals.
ID | Tier | KPI | Definition | Target (MVP validation) | How to measure | Why it matters
K1 | Primary | Straight-through extraction accuracy | % of documents (of supported types) whose extracted JSON is correct with no manual fix. | ≥ 80% | Periodic sample audit of processed docs vs. a hand-checked ground truth set. | Validates that the AI core actually delivers usable structured data.
K2 | Primary | Retrieval success & speed | % of searches where the user opens a result, plus the median time-to-result. | ≥ 70% search→open; < 2s median | Search and result-click logs in the app. | Tests the core archive promise: users find their files fast and accurately.
K3 | Primary | Cost per document processed | All-in cost (storage + compute + GPU) divided by documents processed. | Below your target threshold (set the baseline in Sprint 5). | Monthly cloud bill ÷ count of documents processed. | Directly tests the stated #1 priority: cost-efficiency.
K4 | Secondary | Processing success rate | % of uploads that complete the pipeline without error. | ≥ 95% | Pipeline / worker job logs. | Reliability signal for ingestion; high failure rates erode trust.
K5 | Secondary | Pilot engagement | Documents uploaded per week by the pilot client over the first ~4 weeks. | Sustained or growing. | Usage analytics per tenant. | Real-world signal that the product is genuinely useful.